## Slide 1: Software Construction
Department of Computer Science
Quaid-i-Azam University
Chapter 31-35 Pressman
ISO/IEC/IEEE 16326-2019 guideline

## Slide 2: Learning Outcomes
Apply understanding of the activities involved in project planning to develop a project plan according to the ISO/IEC/IEEE 16326-2019 guideline
Explain the purpose of and activities in reviews and develop a review checklist for plan and for work products developed during the software development process

## Slide 3: ISO/IEC/IEEE 16326
Standard provides normative content specifications for project management plans concerned with systems, and software systems
This document is intended to aid project managers in managing to successful conclusion those projects concerned with systems, including software systems

## Slide 4: Plan Contents for you
Front Matter
1. Project overview
  Project summary
  Purpose, scope and objectives …….………………………………..……..
  Assumptions and constraints …………..………………………………..….
  Project deliverables …………………………….……………......................
  Schedule summary …………….…………….........................
2. References ……………………………………………………………………….......................
3. Definitions …………………………………………………………………………………..…….
4. Project context ……………..…………………………………………………….......................
  Process model …………………………………………………………………………...
  Methods, tools and techniques ………………………………………………………...
  Product acceptance plan ………………………………………………………….…….
5. Project planning.………………….……………………………………………………………….
  Project work plans ………………………….…………………………………………....
  Work activities ……………………………………………………………….....
  Schedule allocation ………………………………………………………...….
  Resource allocation ………………………………………………………..….
8. Supporting process plans ………………………………………………………………...……..
Risk management ……………………………….……………………………………….

## Slide 5: The Project
Projects get into trouble when …
  Software people don’t understand their customer’s needs.
  The product scope is poorly defined.
  Changes are managed poorly.
  Deadlines are unrealistic.
  The project team lacks people with appropriate skills.
  Managers [and practitioners] avoid best practices and lessons learned.

## Slide 6: Common-Sense Approach to Projects
Start on the right foot.
  This is accomplished by working hard (very hard) to understand the problem that is to be solved and then setting realistic objectives and expectations.
Maintain momentum.
  The project manager must provide incentives to keep turnover of personnel to an absolute minimum, the team should emphasize quality in every task it performs, and senior management should do everything possible to stay out of the team’s way.
Track progress.
  For a software project, progress is tracked as work products (e.g., models, source code, sets of test cases) are produced and approved (using formal technical reviews) as part of a quality assurance activity.
Make smart decisions.
  In essence, the decisions of the project manager and the software team should be to “keep it simple.”
Conduct a postmortem analysis.
  Establish a consistent mechanism for extracting lessons learned for each project.

## Slide 7: What is Scope?
Software scope describes
  the functions that are to be delivered to end-users
  the data that are input and output
  the project constraints that bound the system.

## Slide 8: Scope
Context. How does the software to be built fit into a larger system, product, or business context, and what constraints are imposed as a result of the context?
Information objectives. What customer-visible data objects are produced as output from the software? What data objects are required for input?
Function and performance. What function does the software perform to transform input data into output? Are any special performance characteristics to be addressed?

## Slide 9: Scope (IEEE std. 830-1998)
Identify the software product(s) to be produced by name (e.g., Host DBMS, Report Generator, etc.)
Describe the application of the software being specified, including relevant benefits, objectives, and goals
Explain what the software product(s) will, and, if necessary, will not do

## Slide 10: Schedule Tracking
  conduct periodic project status meetings in which each team member reports progress and problems.
  evaluate the results of all reviews conducted throughout the software engineering process.
  determine whether formal project milestones have been accomplished by the scheduled date.
  compare actual start-date to planned start-date for each project task listed in the resource table
  meet informally with practitioners to obtain their subjective assessment of progress to date and problems on the horizon.
  use earned value analysis to assess progress quantitatively.

## Slide 11: Earned Value Analysis
The budgeted cost of work scheduled (BCWS)
BCWSi is the effort planned for work task i
BAC = Σ(BCWSk ) for all tasks k
The budgeted cost of work performed (BCWP)
Schedule performance index, SPI = BCWP/BCWS
Schedule variance, SV = BCWP – BCWS
The actual cost of work performed (ACWP)
Cost performance index, CPI = BCWP/ACWP
Cost variance, CV = BCWP - ACWP

## Slide 12: What Are Reviews?
a meeting conducted by technical people for technical people
a technical assessment of a work product created during the software engineering process
a training ground

## Slide 13: Conducting the Review
be prepared—evaluate
product before the review
review the product, not
the producer
keep your tone mild, ask
questions instead of
making accusations
stick to the review agenda
raise issues, don't resolve them
avoid discussions of style—stick to technical
correctness
schedule reviews as project tasks
record and report all review results
1.
2.
3.
4.
5.
6.
7.
8.

## Slide 14: The Review/Inspection Process

## Slide 15: Example Planning Data
Copyright © 1998 Philip M. Johnson

## Slide 16: Example Review Meeting Data
Copyright © 1998 Philip M. Johnson

## Slide 17: Reviews, Inspections and Walkthroughs
A review is simply an examination of a work product by people other than those who produced it
An inspection (called a formal technical review) is a disciplined activity where people are assigned roles
Inspections are also sometimes called walkthroughs. However, in a walkthrough, the author of the artifact describes the product and asks for comments

## Slide 18: Advantages of Inspections
18
Adapted from Software Engineering A Practitioner’s Approach by R.S. Pressman
Inspections may focus on source code, but may also include any representation of system
Greater than 60% errors in programs can be detected by informal inspections
This figure increases to greater than 90% with formal approaches
  A single inspection session can reveal many errors
  Incomplete versions can be inspected without additional cost
  Broader quality attributes can be tested

## Slide 19: Risk
Involves two characteristics
  Uncertainty
  Loss

## Slide 20: Risk
Involves two characteristics
  Uncertainty
  Loss
What can go wrong?
What is the likelihood?
What will the damage be?
What can we do about it?

## Slide 21: Risk Management Paradigm
RISK
control
identify
analyze
plan
track

## Slide 22: Risk Categories
Project risks
Technical risks
Business Risks
General categories
  Generic
  Product Specific

## Slide 23: Building a Risk Table
Risk
Probability
Impact
RMMM
Risk
Mitigation
Monitoring
&
Management

## Slide 24: Acceptance Tests
Acceptance tests describe the criteria by which stakeholders will determine whether the system meets their needs
Business rules, non-functional requirements, and usage requirements can be captured as acceptance tests
Acceptance tests are sometimes called "conditions of satisfaction“
  Adapted from http://www.agilemodeling.com/artifacts/acceptanceTests.htm

## Slide 25: Acceptance Test Template
Must include the following information
  Brief description of what capabilities are being tested ("this test will verify that reserve seat functionality works as described in requirements XX, YY, ZZ")
  Which requirements are being verified by this test
  Test setup/pre-conditions
  Test steps
  Expected results

## Slide 26: Acceptance Test Template
ID | T0014
Description | Checking accounts have an overdraft limit of $500. As long as there are sufficient funds (e.g. -$500 or greater) within a checking account after a withdrawal has been made the withdrawal will be allowed.
Setup | Create account 12345 with an initial balance of $50 Create account 67890 with an initial balance of $0
Instructions | Withdraw $200 from account #12345 Withdraw $350 from account #67890 Deposit $100 into account #12345 Withdraw $200 from account #67890 Withdraw $150 from account #67890 Withdraw $200 from account #12345 Deposit $50 into account #67890 Withdraw $100 from account #67890

## Slide 27: Acceptance Test Template
Expected Results | Account #12345: Ending balance = -$250 $200 Withdrawal transaction posted against it $100 Deposit transaction posted against it $200 Withdrawal transaction posted against it Account #67890: Ending balance = -$500 $350 Withdrawal transaction posted against it $150 Withdrawal transaction posted against it $50 Deposit transaction posted against it Errors logged: Insufficient funds in Account #67890 (balance -$350) for $200 Withdrawal Insufficient funds in Account #67890 (balance -$450) for $100 Withdrawal

## Slide 28
For usage testing, a simpler format may be followed
  A [named user role] can [select/operate] [feature/function]